## Tracker
Project Name |  | BRMS Website |  |  | Project Manager |  | Swapnil Wale |  |  | Project Timeline
# | Component | Analysis | Design | Build | Tcase | QA | UA | Impl | Status | Project Phase | Start | End | Status
1 | Home Page | 100% | 100% | 100% | 100% | 80% |  |  | On track | Analysis | 2016-01-01 | 2016-02-15 | Complete
2 | Login Page | 100% | 100% | 100% | 100% | 75% |  |  | On track | Design | 2016-02-15 | 2016-03-05 | Concern
3 | Admin Module | 100% | 100% | 95% | 100% |  |  |  | On track | Build | 2016-03-06 | 2016-04-15 | Delayed
4 | Registration Module | 100% | 100% | 75% | 100% |  |  |  | On track | Testing | 2016-04-15 | 2016-05-15 | Delayed
5 | Loan Module | 100% | 100% | 60% | 100% |  |  |  | Concern | User Accpetance | 2016-05-16 | 2016-06-25 | Pending
6 | Integration Module | 100% | 75% |  | 100% |  |  |  | Delayed | Implementation | 2016-06-25 | 2016-07-02 | Pending
7 | Accounting Module | 100% | 50% |  | 100% |  |  |  | De-scoped
8 | Payment Gateway | 100% | 10% |  | 100% |  |  |  | On hold
Project Team
Suman - Analysis Beth, Max - Design and Development Ruby - Testing Alex - UA

## Data
Status
Pending
On track
Delayed
Concern
Complete
De-scoped
On hold