## Velocity
Project: | Coffee shop build |  | Updated By: | Cynthia Lin
PM: | Antonio Mendez |  | Update Date: | 2017-12-18
Features |  | Actual Points |  |  |  |  | Comments
Name | Points | Sprint #5 | Sprint #4 | Sprint #3 | Sprint #2 | Sprint #1
Sign the lease on the building | 10 | 10 | 0 | 0 | 0 | 0
Complete the dry walling | 25 | 10 | 15 | 0 | 0 | 0
Paint the walls | 10 | 0 | 0 | 10 | 0 | 0
Install the appliances | 35 | 5 | 15 | 15 | 0 | 0
Procure the furniture | 15 | 0 | 0 | 10 | 5 | 0
Complete the staffing | 25 | 5 | 5 | 5 | 5 | 5
Laminate the menus | 5 | 0 | 0 | 0 | 0 | 5
Sign contracts with local vendors | 30 | 0 | 15 | 5 | 10 | 0
Launch a social media ad campaign | 36 | 8 | 8 | 8 | 0 | 12 | A snag on sprint #2 was fixed on sprint #1
Install the neon signs | 17 | 0 | 0 | 0 | 5 | 12
Complete the interior design | 22 | 0 | 0 | 10 | 8 | 4
Baseline Points | 230 | 184 | 138 | 92 | 46 | 0 | Assumed linear achievement of points
Actual Points | 230 | 192 | 134 | 71 | 38 | 0
Velocity Points |  | 38 | 58 | 63 | 33 | 38
Commentary: The project started behind the planned points, but was able to catch up at the end of the 4th sprint, and since then has been ahead of the plan. The green velocity line denotes the number od points achieved in each sprint.