## How to Use
How to Use — Risk Register
by ExcelGuru.io ¦ Turn 'what could go wrong' into a scored, ranked, owned list you can act on.
What this template does
Capture each project risk, score it on likelihood and impact, and let the register rank it from Low to High so you know where to focus.
Sheet 1 — Risk Register
Describe the risk, pick a category, and rate likelihood and impact from 1 to 5. 'Score' and 'Level' calculate automatically, and each risk gets an owner and a mitigation plan.
How scoring works
Score is Likelihood x Impact, the classic risk-matrix approach. A nested IF then bands it: 15+ is High, 8-14 is Medium, below 8 is Low — colour-coded so the dangerous ones jump out.
Sheet 2 — Dashboard
See how many high risks you carry, your average and top score, what's open versus being mitigated, and the spread across categories.
Make it yours
Edit categories, owners and statuses on the Lists tab. Sort by Score, descending, and your risk review meeting writes its own agenda.

## Dashboard
RISK REGISTER — DASHBOARD
Total Risks |  | High Risks |  | Avg Score | Open Risks
10 |  | 2 |  | 11 | 4
Mitigating |  | Top Score
4 |  | 16
Risks by Level |  |  | Risks by Category
Level | Count |  | Category | Count
High | 2 |  | Financial | 2
Medium | 7 |  | Operational | 2
Low | 1 |  | Technical | 2
|  |  | Legal | 1
|  |  | People | 2
|  |  | External | 1

## Risk Register
Risk Register — score, rank and manage every project risk
ID | Risk | Category | Likelihood | Impact | Score | Level | Owner | Mitigation | Status
R-01 | Key supplier delays delivery | Operational | 4 | 4 | 16 | High | Sam | Dual-source critical parts | Open
R-02 | Budget overrun on build | Financial | 3 | 5 | 15 | High | Maria | Weekly burn review | Mitigating
R-03 | Lead developer leaves | People | 2 | 5 | 10 | Medium | Alex | Document & cross-train | Mitigating
R-04 | Data breach | Technical | 2 | 5 | 10 | Medium | Priya | Pen test + encryption | Open
R-05 | Scope creep from client | Operational | 4 | 3 | 12 | Medium | Priya | Change-control process | Mitigating
R-06 | Regulatory change | Legal | 2 | 4 | 8 | Medium | Maria | Quarterly legal review | Open
R-07 | Server downtime | Technical | 3 | 4 | 12 | Medium | Sam | Failover + monitoring | Mitigating
R-08 | Competitor launch | External | 3 | 3 | 9 | Medium | Alex | Accelerate roadmap | Accepted
R-09 | Currency fluctuation | Financial | 3 | 2 | 6 | Low | Maria | Hedge large orders | Accepted
R-10 | Team burnout | People | 3 | 4 | 12 | Medium | Jordan | Workload caps + time off | Open

## Lists
Category | Status | Owner | Score 1-5
Financial | Open | Alex | 1
Operational | Mitigating | Priya | 2
Technical | Closed | Sam | 3
Legal | Accepted | Maria | 4
People |  | Jordan | 5
External