## How to Use
How to Use — Event Planning Checklist
by ExcelGuru.io ¦ ExcelGuru.io ¦ Plan every detail and keep your event on budget
1. List every task
Add each job, from booking the venue to ordering flowers, with a category.
2. Set owners and dates
Assign an owner and a due date. Days Left counts down so nothing is left too late.
3. Budget as you go
Add a cost estimate to each task, so the running total keeps your event on budget.
4. Track to the big day
Update statuses and watch the percent complete climb toward your event.

## Dashboard
Event Planning Checklist — Dashboard
Total Tasks | Done | To Do | Overdue
6 | 1 | 5 | 2
Total Cost Est. | % Complete
2660 | 16.67%

## Tasks
Event Planning Checklist
ExcelGuru.io ¦ Plan every detail and keep your event on budget
Task | Category | Owner | Due Date | Status | Days Left | Cost Est. | Notes
Book venue | Venue | Me | 2026-05-25 | Done |  | 1200 | Deposit paid
Send invitations | Guests | Me | 2026-06-12 | In Progress | -2 | 80 | Online
Confirm caterer | Catering | Partner | 2026-06-19 | Not Started | 5 | 950 | 3 quotes in
Order flowers | Decor | Me | 2026-06-26 | Not Started | 12 | 180
Finalise guest list | Guests | Me | 2026-06-13 | In Progress | -1 | 0 | Chasing RSVPs
Arrange transport | Admin | Partner | 2026-07-04 | Not Started | 20 | 250
Formulas:
Days Left = IF(OR([Due Date]="",[Status]="Done"),"",[Due Date]-TODAY())

## Lists
Lists — edit these to customise dropdowns
Category | Status
Venue | Not Started
Catering | In Progress
Guests | Done
Decor
Admin