## Sheet1
Sample Advertising Gantt Chart
Start Date | 2021-06-01 |  |  |  | Week 1 | [5 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
 | time axis 2021-06-01 to 2021-07-18
Actitvity | Responsible | Start Date | End Date | Progress | time axis 2021-06-01 to 2021-07-18
Initial Meetings | Louis Moran | 2021-06-01 | 2021-06-07 | 60%
Review Policies & Objectives | Nathan Adams | 2021-06-08 | 2021-06-14 | 80%
Requirements | Vernon Roberts | 2021-06-14 | 2021-06-19 | 45%
Plan of Action Execution | Jacob Black | 2021-06-20 | 2021-06-30 | 80%
Testing | Ryan Kim | 2021-06-29 | 2021-07-18 | 90%