## PRINCE2 Log
| Project: | SAP upgrade
| Issues Log Owner: | Manny Hernandez
Issue ID | Issue Type (RFC / OS / P) | Date Raised | Raised By | Issue Report Author | Description | Priority | Severity | Status | Date of Last Update | Closure Date
1 | RFC | 2018-01-04 | Walter Gust | Manny Hernandez | Change the Logistics module to include DHL as a vendor | High | Major | Not Started | 2018-01-10 | N/A
2 | P | 2018-01-04 | Sheila Kahn | Manny Hernandez | The coffee makers are corroded and take forever to boil the water | Low | Minor | In Process | 2018-01-10 | N/A
3 | P | 2018-01-05 | Bethany Oliver | Manny Hernandez | The site response times are slow and may require a HW upgrade soon | Medium | Minor | Done | 2018-01-10 | 2018-01-08
4 | RFC | 2018-01-08 | Brooke Hall | Manny Hernandez | Change the Finance module to allow for Quarterly reports (not just monthly and yearly) | Medium | Minor | Cancelled | 2018-01-10 | 2018-01-09
5 | OS | 2018-01-08 | Stacey Lev | Manny Hernandez | The specification for the server was: 23X12X8 Inches. The one delivered is 28X12X8 and doesn't fit in the rack | High | Major | Not Started | 2018-01-10 | N/A
6 | RFC | 2018-01-08 | Homer R. Black | Manny Hernandez | Change the Business Intelligence report to include pie charts of budget used vs. allocated | Medium | Major | In Process | 2018-01-10 | N/A
7 | P | 2018-01-09 | Matt Christenson | Manny Hernandez | The team lead for the PMO's took up new responsibilities in the Logistics team and is over worked | Medium | Major | In Process | 2018-01-10 | N/A
8 | P | 2018-01-09 | Mare Winthrop | Manny Hernandez | The budget doesn't allow for recruiting a new Human Resources representative as agreed | Low | Minor | In Process | 2018-01-10 | N/A
9 | P | 2018-01-09 | Henry Kufic Jr. | Manny Hernandez | The new computer monitors aren't compatible with the design division's computers | Medium | Major | In Process | N/A | N/A
10 | RFC | 2018-01-11 | Miles Johnson | Olivia Tane | Change the Manufacturing module to allow use of the new pressing machine ordered | Medium | Minor | Done | N/A | 2018-01-11
11 | RFC | 2018-01-11 | Andre Flares | Olivia Tane | Change the Procurement module to allow use of foreign currency | Medium | Minor | Cancelled | N/A | 2018-01-11
Issue Type Legend
| RFC | Request for Change
| OS | Off-Specification
| P | Problem / Concern

## Agile Log
Project Details
Project: | Hiking Routes | Updated by: | Greg Michaels
Sprint Master: | Greg Michaels | Updated on: | 2018-02-11
Issue Log
Number | Issue | Related To Sprint | Assigned To | Feature Affected | Sprint Due Date | Status | Comments
1 | The layering is available only on the smart phone app, not the website | Sprint #1 | Terry Chanda | Map layering ability | 2018-01-05 | Done
2 | If the GPS is turned on after the app was opened, it doesn't calibrate the position | Sprint #1 | Wade Harper | GPS compatibility | 2018-01-05 | Done
3 | The standard security protocols aren't enough for the US regulations | Sprint #1 | Jane Kettering | Secure credit card payment | 2018-01-05 | Behind Schedule | We hired a security expert to assist with updating the protocols. Planned to be updated by 16-Jan
4 | Once marked, the map can't return to its original layer | Sprint #1 | Samantha Wilde | Marketing a map | 2018-01-05 | Cancelled | We decided to eliminate the marking option, it was hardly used
5 | Can only share with peers who have an example domain E-mail address | Sprint #1 | Kylie McDermott | Peer sharing | 2018-01-05 | Behind Schedule | The solution will be to open the sharing option with all domains. Planned to be done by 12-Jan
6 | Only pop-ups on a smart phone, not the computer / tablet | Sprint #2 | Terry Chanda | Advertisement pop-ups | 2018-01-26 | On Schedule
7 | Only the app admins can add information to existing businesses | Sprint #2 | Wade Harper | Adding info to existing businesses | 2018-01-26 | On Schedule
8 | Only the app admins can add a new route | Sprint #2 | Shaun Rogue | Creating a new route | 2018-01-26 | On Schedule
9 | Peer sharing is available only to the users' followers, not to all members | Sprint #2 | Emily Bartholomew | Sharing the new route | 2018-01-26 | Behind Schedule | Once the sharing option will be in place, this issue will be resolved. Planned to be done by 12-Jan
10 | Once a new route is planned it is available only to the creator | Sprint #3 | Samantha Wilde | Inviting friends to join routes | 2018-02-23 | On Schedule
11 | Only one user can pay for the route planning | Sprint #3 | Kylie McDermott | Joint payment | 2018-02-23 | Cancelled | We will buy a payment sharing feature from the Citibank app
12 | The route which was recorded can't be exported and shared | Sprint #3 | Emily Bartholomew | Sharing the actual route on the map | 2018-02-23 | On Schedule