## Sheet1
Recruitment Gantt Chart
Start Date | 2021-02-01 |  |  |  |  | 1 W | [6 empty] | 2 W | [6 empty] | 3 W | [6 empty] | 4 W | [6 empty] | 5 W | [6 empty] | 6 W | [6 empty] | 7 W | [6 empty] | 8 W
 | time axis 2021-02-01 to 2021-03-28
Task Name | Srat Date | End Date | Duration | Progress | Status | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Requirements Analysis & Planning | 2021-02-01 | 2021-02-13 | 13 | 30% | Ongoing
Strategy Development | 2021-02-08 | 2021-02-21 | 14 | 20% | Ongoing
Execution | 2021-02-22 | 2021-03-21 | 27 | 60% | Ongoing
Induction | 2021-03-22 | 2021-03-28 | 7 | 20% | Ongoing