## How to Use
How to Use — Project Timeline
by ExcelGuru.io ¦ ExcelGuru.io ¦ Plan phases, dates and progress on one timeline
1. List your tasks and phases
Enter each task and assign it to a phase such as Planning or Build.
2. Add start and end dates
Set each task's dates in the amber cells. Duration calculates automatically.
3. Track status and progress
Update the status and the percent complete as work moves along.
4. Read the dashboard
Average percent complete shows momentum, and the latest end date shows your finish.

## Dashboard
Project Timeline — Dashboard
Total Tasks | Completed | In Progress | Avg % Complete
6 | 2 | 2 | 45.83%
Total Days | Latest End Date
58 | 2026-07-03

## Timeline
Project Timeline
ExcelGuru.io ¦ Plan phases, dates and progress on one timeline
Task | Phase | Owner | Start Date | End Date | Duration (days) | Status | % Complete
Requirements gathering | Planning | Alex | 2026-05-24 | 2026-05-30 | 7 | Done | 1
Wireframes & design | Design | Jordan | 2026-05-31 | 2026-06-08 | 9 | Done | 1
Front-end build | Build | Sam | 2026-06-09 | 2026-06-23 | 15 | In Progress | 0.45
Back-end build | Build | Priya | 2026-06-09 | 2026-06-25 | 17 | In Progress | 0.3
Testing & QA | Test | Alex | 2026-06-24 | 2026-07-01 | 8 | Not Started | 0
Launch | Launch | Sam | 2026-07-02 | 2026-07-03 | 2 | Not Started | 0

## Lists
Lists — edit these to customise dropdowns
Phase | Status | Owners (sample)
Planning | Not Started | Alex
Design | In Progress | Sam
Build | Done | Jordan
Test | Blocked | Priya
Launch