## How to Use
How to Use — Meeting Minutes & Action Log
by ExcelGuru.io ¦ Capture decisions and the actions that follow — and actually chase them down.
What this template does
Keep a running log of every meeting's decisions, and a linked list of the action items that come out of them, each with an owner and a due date.
Sheet 1 — Meeting Log
Record the date, meeting, who attended and the key decisions. This is your searchable history of what was actually agreed.
Sheet 2 — Action Items
List each action with an owner, the meeting it came from, and a due date. 'Days Left' counts down and goes red when overdue; done items drop out of the count.
Sheet 3 — Dashboard
See meetings logged, open versus completed actions, what's overdue, and how the workload is split across owners.
Make it yours
Edit the owners and statuses on the Lists tab. Sort Action Items by Days Left before each meeting so the first agenda item is always 'what's overdue?'.

## Dashboard
MEETINGS & ACTIONS — DASHBOARD
Meetings Logged |  | Action Items | Open Actions | Overdue Actions
6 |  | 8 | 5 | 0
Completed |  | Completion %
3 |  | 37.5%
Actions by Owner
Owner | Actions
Alex | 1
Priya | 2
Sam | 2
Jordan | 2
Maria | 1

## Meeting Log
Meeting Minutes & Notes Log — decisions and actions, never lost again
Date | Meeting | Attendees | Key Decisions / Notes | Chair
2026-05-24 | Weekly Standup | Whole team | Agreed Q3 priorities; deferred hiring | Alex
2026-05-30 | Client Review | Alex, Priya, Client | Client approved phase 1; scope add requested | Priya
2026-06-03 | Product Planning | Product team | Roadmap locked for next sprint | Sam
2026-06-06 | Budget Review | Leads | Marketing budget +10%; freeze travel | Maria
2026-06-10 | Retrospective | Whole team | Improve handoffs; add QA checklist | Jordan
2026-06-12 | Standup | Whole team | Blocker on API; Sam to escalate | Alex

## Action Items
Action Items
Action | Owner | From Meeting | Due Date | Status | Days Left
Send Q3 priorities doc | Alex | Weekly Standup | 2026-06-11 | Done
Draft scope-change quote | Priya | Client Review | 2026-06-15 | In Progress | 2
Finalise sprint backlog | Sam | Product Planning | 2026-06-14 | In Progress | 1
Update budget sheet | Maria | Budget Review | 2026-06-12 | Done
Write QA checklist | Jordan | Retrospective | 2026-06-17 | Open | 4
Escalate API blocker | Sam | Standup | 2026-06-13 | In Progress | 0
Book client demo | Priya | Client Review | 2026-06-19 | Open | 6
Share retro notes | Jordan | Retrospective | 2026-06-10 | Done
Formulas:
Days Left = IF(OR([Due Date]="",[Status]="Done"),"",[Due Date]-TODAY())

## Lists
Status | Owner
Open | Alex
In Progress | Priya
Done | Sam
Blocked | Jordan
Maria