## How to Use
How to Use — Renovation Punch List
by ExcelGuru.io ¦ ExcelGuru.io ¦ Snag, cost and sign off every renovation job
1. List every snag
Walk each room and log every job, with its room and the trade needed.
2. Prioritise and cost
Set a priority and an estimated cost, so you can budget and sequence the work.
3. Track progress
Update the status as jobs move from Open to Done, and sign off completed work.
4. Watch the budget
The dashboard totals your estimated costs and shows how much is still outstanding.

## Dashboard
Renovation Punch List — Dashboard
Total Items | Done | Outstanding | High Priority
5 | 1 | 4 | 2
Total Cost Est. | Signed Off
205 | 1

## Punch List
Renovation Punch List
ExcelGuru.io ¦ Snag, cost and sign off every renovation job
Item | Room | Trade | Priority | Cost Est. | Status | Sign-off | Notes
Touch up paint on landing | Hallway | Painting | Low | 40 | Open | No
Fix dripping tap | Bathroom | Plumbing | High | 80 | In Progress | No | Plumber booked
Replace cracked socket | Kitchen | Electrical | High | 60 | Open | No | Safety
Re-hang wardrobe door | Bedroom | Carpentry | Medium | 0 | Done | Yes | Done by us
Seal around bath | Bathroom | General | Medium | 25 | Open | No

## Lists
Lists — edit these to customise dropdowns
Trade | Priority | Status
Plumbing | High | Open
Electrical | Medium | In Progress
Painting | Low | Done
Carpentry
General