## Sheet1
SWOT Analysis Gantt Chart
Sl No. | Activity Item | Lead | Progress | Status
1 | Set & Communicate Objectives | Opal Mullins | 100% | Completed
2 | Research Phase | Shawn Scott | 80% | Ongoing
3 | List of Business's Strengths | Sam Gibbs | 40% | Ongoing
4 | List of Business's Weaknesses | Ollie Holt | 100% | Completed
5 | List of Potential Opportunities | Virgil Black | 50% | Ongoing
6 | List of Potential Threats | Tim Castro | 0% | Upcoming