## Sheet1
HR Gantt Chart
Start Date | 2021-02-01 |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
 | time axis 2021-02-01 to 2021-03-21
Task Name | Start Date | End Date | Progress | Status | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Requirements Analysis | 2021-02-01 | 2021-02-10 | 60% | Ongoing
Employee Recruitment & Selection | 2021-02-08 | 2021-02-15 | 40% | Ongoing
Training & Development Strategy | 2021-02-15 | 2021-02-28 | 100% | Completed
Performance Management Strategy | 2021-03-01 | 2021-03-10 | 50% | Ongoing
Review & Modify Policies | 2021-03-08 | 2021-03-21 | 0% | upcoming