## How to Use
How to Use — Task Tracker
by ExcelGuru.io ¦ ExcelGuru.io ¦ Track every task, owner, due date and status in one place
1. List your tasks
Add each task with its owner, priority and due date.
2. Set the status
Use the dropdown to mark each task Not Started, In Progress, Done or Blocked, and enter its % complete.
3. Watch the deadlines
Days Left counts down to each due date. Overdue tasks are flagged on the dashboard.
4. Track progress
The dashboard shows how many tasks are done, in progress, overdue or blocked, and the average completion.

## Dashboard
Task Tracker — Dashboard
Total Tasks | Completed | In Progress | Overdue
8 | 1 | 2 | 2
Avg % Complete | Blocked
26.25% | 1

## Tasks
Task Tracker
ExcelGuru.io ¦ Track every task, owner, due date and status in one place
Task | Owner | Priority | Due Date | Status | % Complete | Days Left
Draft project brief | Sam | High | 2026-06-16 | Done | 100%
Stakeholder interviews | Priya | High | 2026-06-19 | In Progress | 60% | -2
Design wireframes | Alex | Medium | 2026-06-24 | In Progress | 30% | 3
Set up dev environment | Jordan | Medium | 2026-06-22 | Not Started | 0% | 1
Content plan | Priya | Low | 2026-06-20 | Blocked | 20% | -1
Build landing page | Alex | High | 2026-06-28 | Not Started | 0% | 7
QA test plan | Sam | Medium | 2026-07-01 | Not Started | 0% | 10
Launch checklist | Jordan | Low | 2026-07-05 | Not Started | 0% | 14
Formulas:
Days Left = IF(OR([Task]="",[Status]="Done"),"",[Due Date]-TODAY())

## Lists
Lists — edit these to customise dropdowns
Priority | Status
High | Not Started
Medium | In Progress
Low | Done
Blocked