## How to Use
How to Use — Project Task Tracker
by ExcelGuru.io ¦ Run any project from one sheet — who's doing what, by when, and how far along.
What this template does
Track every task across the project's phases with an owner, priority, due date and progress, then roll it all up into a clear status dashboard.
Sheet 1 — Task Tracker
Add each task, assign a phase and owner, set a due date and update the status and % complete as work moves. 'Days Left' counts down and flags overdue tasks in red.
Sheet 2 — Dashboard
See totals, completion, what's overdue, average progress, and the spread of work across statuses and phases.
Reading the numbers
Average % complete gives a quick health check on the whole project, while the overdue and due-this-week counts tell you where to push next.
Make it yours
Edit phases, owners, priorities and statuses on the Lists tab. Filter by owner for one-on-ones, or by phase to run a focused stand-up.

## Dashboard
PROJECT TASKS — DASHBOARD
Total Tasks |  | Completed |  | In Progress | Overdue
14 |  | 3 |  | 3 | 1
Avg % Complete |  | Due This Week
35.7143 |  | 3
Tasks by Status |  |  | Tasks by Phase
Status | Count |  | Phase | Count
Not Started | 7 |  | Planning | 2
In Progress | 3 |  | Design | 2
Blocked | 1 |  | Build | 5
Done | 3 |  | Testing | 3
|  |  | Launch | 2

## Task Tracker
Project Task Tracker — every task, owner and deadline in one view
Task | Phase | Owner | Priority | Due Date | Status | % Complete | Days Left
Define requirements | Planning | Alex | High | 2026-06-03 | Done | 100
Stakeholder sign-off | Planning | Maria | High | 2026-06-08 | Done | 100
Wireframes | Design | Priya | High | 2026-06-11 | Done | 100
UI mockups | Design | Priya | Medium | 2026-06-16 | In Progress | 60 | 3
Database schema | Build | Sam | High | 2026-06-15 | In Progress | 70 | 2
API endpoints | Build | Sam | High | 2026-06-19 | In Progress | 40 | 6
Frontend build | Build | Jordan | Medium | 2026-06-23 | Not Started | 0 | 10
Integration | Build | Jordan | Medium | 2026-06-27 | Not Started | 0 | 14
Test plan | Testing | Maria | Medium | 2026-06-21 | Not Started | 0 | 8
QA pass | Testing | Maria | High | 2026-06-29 | Not Started | 0 | 16
Bug fixes | Testing | Sam | High | 2026-07-01 | Not Started | 0 | 18
Launch prep | Launch | Alex | High | 2026-07-03 | Not Started | 0 | 20
Go live | Launch | Alex | High | 2026-07-04 | Not Started | 0 | 21
Payment bug | Build | Sam | High | 2026-06-12 | Blocked | 30 | -1
Formulas:
Days Left = IF(OR([Due Date]="",[Status]="Done"),"",[Due Date]-TODAY())

## Lists
Phase | Owner | Priority | Status
Planning | Alex | High | Not Started
Design | Priya | Medium | In Progress
Build | Sam | Low | Blocked
Testing | Jordan |  | Done
Launch | Maria